## Sheet1
Carrot Quest ASSET LIST
Department | Asset | Task | Who | Due | Priority | Status | KEY
ART | Vagabond Bunny | Walk animation front | Joy | Week 5 | High | Incomplete | Incomplete
ART | Vagabond Bunny | Walk animation back | Joy | Week 5 | High | Incomplete | Complete
ART | Vagabond Bunny | Walk animation side | Joy | Week 5 | High | Incomplete | OVERDUE
ART | Grasslands Tileset | Create ground tiles | Joy | Week 6 | High | Incomplete
ART | Grasslands Tileset | Create trees | Joy | Week 6 | High | Incomplete
ART | Grasslands Tileset | Create fences | Joy | Week 6 | High | Incomplete
ART | Grasslands Tileset | Create lake | Joy | Week 6 | Low | Incomplete
ART | Bullet Bunny Enemy | Create idle sprite | Joy | Week 7 | High | Incomplete
ART | Bullet Bunny Enemy | Walk animation front | Joy | Week 7 | High | Incomplete
ART | Bullet Bunny Enemy | Walk animation back | Joy | Week 7 | High | Incomplete
ART | Bullet Bunny Enemy | Walk animation side | Joy | Week 7 | High | Incomplete
ART | Slime? Enemy | Create idle sprite | Joy | Week 8 | High | Incomplete
ART | Slime? Enemy | Walk animation front | Joy | Week 8 | High | Incomplete
ART | Slime? Enemy | Walk animation back | Joy | Week 8 | High | Incomplete
ART | Slime? Enemy | Walk animation side | Joy | Week 8 | High | Incomplete
ART | Bear Bunny Enemy | Create idle sprite | Joy | Week 9 | High | Incomplete
ART | Bear Bunny Enemy | Walk animation front | Joy | Week 9 | High | Incomplete
ART | Bear Bunny Enemy | Walk animation back | Joy | Week 9 | High | Incomplete
ART | Bear Bunny Enemy | Walk animation side | Joy | Week 9 | High | Incomplete
ART | Bear Bunny Enemy | Attack animation | Joy | Week 9 | High | Incomplete
ART | Bunnyville House | Art of a house in Bunnyville. | Joy | Week 10 | Low | Incomplete
ART | Revolver item art | Art for the revolver weapon. | Joy | Week 11 | Low | Incomplete
ART | Slingshot item art | Art for the slingshot weapon. | Joy | Week 11 | Low | Incomplete
ART | Carrot Powerup Art | Art for the carrot powerup. Grows from the ground. | Joy | Week 11 | Low | Incomplete
ART | UI Buttons | UI art for the buttons on the menus and dialogue screens. | Joy | Week 12 | Low | Incomplete
ART | UI Text Display | UI art for text boxes - instructions, dialogue, inventory, etc. | Joy | Week 12 | Low | Incomplete
ART | Title Art for Main Menu | Title art for Carrot Quest: The Root of Evil. Incorporate carrot/bunny/woodsy elements. | Joy | Week 13 | Low | Incomplete
ART | Vagabond Bunny | Player death animation. Falls to floor. | Joy | Week 14 | Low | Incomplete
PROGRAMMING | Camera Scale | Fix camera to have larger graphics than pixel, adjust physics/knockback/sizes to new camera size | Brenton | Week 5 | High | Incomplete
PROGRAMMING | Gun Attack Fire Rate | Implement a limited gun fire rate (ideally adjustable per weapon), limited bullets, reload | Brenton | Week 6 | High | Incomplete
PROGRAMMING | Reload Action | A function to press 'R' to reload the gun. Necessary after running out of bullets. | Brenton | Week 6 | High | Incomplete
PROGRAMMING | Dodging Action | Press 'Space' to dodge a short distance in the movement direction. Briefly invulnerable. | Brenton | Week 7 | High | Incomplete
PROGRAMMING | Burrowing Action | Press and hold 'Shift' to create a burrow entrance and enter the ground. On release of 'Shift', burrow exit is created and Player returns to normal state. | Brenton | Week 8 | High | Incomplete
PROGRAMMING | Burrowing Action | While underground (holding down 'Shift'), Player is invulnerable and semi-transparent. | Brenton | Week 8 | High | Incomplete
PROGRAMMING | NPC Interaction | Implement the NPC Hyacinth into the game. When the Player presses 'E' next to an NPC, a dialogue box spawns. | Brenton | Week 9 | High | Incomplete
PROGRAMMING | NPC Dialogue | Once the dialogue box spawns, text will display on it, and the Player can click or press 'E' to advance the dialogue. 'Esc' exits the dialogue. | Brenton | Week 9 | High | Incomplete
PROGRAMMING | NPC Dialogue | While talking to an NPC, the Player can not fire their gun or move. They are invulnerable to attack. | Brenton | Week 9 | High | Incomplete
PROGRAMMING | Healing Carrot Powerup | A carrot growing from the ground that the Player can press 'E' on to consume, giving them 1 heart. | Brenton | Week 10 | High | Incomplete
PROGRAMMING | Enemies Give Up | After the Player gets a certain distance from an aggroed enemy, the enemy stops pursuing them. | Brenton | Week 10 | Low | Incomplete
PROGRAMMING | Slingshot Weapon | A new ranged weapon type added to the game. Hold to aim and release to fire, has a short range. | Brenton | Week 11 | High | Incomplete
PROGRAMMING | Slingshot Weapon | Slingshot weapon is now the starting weapon instead of the revolver. | Brenton | Week 11 | High | Incomplete
PROGRAMMING | Inventory | An inventory system where items can be picked up and then equipped. | Brenton | Week 12 | High | Incomplete
PROGRAMMING | Revolver item pickup | The revolver is an item that can be found, picked up, and then equipped. | Brenton | Week 12 | High | Incomplete
PROGRAMMING | Ultimate Carrot Cannon | The end game weapon, Carrot Quest's master sword. A sacred weapon | Brenton | Week 10 | Low | Incomplete
PROGRAMMING |  |  | Brenton | Week 10 | Low | Incomplete
PROGRAMMING | Enemy Bullets Slower | Enemy bullets slower, more distinct color. Better chance for Player to dodge. | Brenton | Week 13 | Low | Incomplete
SOUND | Bullet Bunny Shoot | A shooting sound for the bullet bunnies, so that the Player can tell when one is shooting at them from afar. | Brenton | Week 7 | High | Incomplete
SOUND | Bullet Bunny Aggro | A monster grunt/squeak-ish sound for when a bullet bunny becomes aggroed to the Player. | Brenton | Week 7 | High | Incomplete
SOUND | Bear Bunny Aggro | A monster growl sound when the bear bunny spots the Player. | Brenton | Week 10 | High | Incomplete
SOUND | Bear Bunny Attack | A monster growl/grunt when the bear bunny does its melee attack. | Brenton | Week 10 | High | Incomplete
SOUND | Slime move sounds | Slime wet sounds that play as it moves. | Brenton | Week 10 | Low | Incomplete
SOUND | Green Fields Music | A looping track for the Fields area, that relatively cheerful. | Brenton | Week 11 | High | Incomplete
SOUND | Slime move sounds | Slime wet sounds that play as it moves. | Brenton | Week 13 | Low | Incomplete
SOUND | Slime move sounds | Slime wet sounds that play as it moves. | Brenton | Week 13 | Low | Incomplete
SOUND | UI interaction / Click | Click sound for interacting with UI. Not very high pitched, kind of a wood sound. | Brenton | Week 13 | Low | Incomplete