## Sheet1
Carrot Quest ASSET LIST
Department | Asset | Task | Who | Due | Priority | Status | KEY
ART | Vagabond Bunny | Walk animation front | Joy | 2023-09-20 | High | Complete | Incomplete
ART | Vagabond Bunny | Walk animation back | Joy | 2023-09-20 | High | Complete | Complete
ART | Vagabond Bunny | Walk animation side | Joy | 2023-09-20 | High | Complete | OVERDUE
ART | Grasslands Tileset | Create ground tiles | Joy | 2023-10-08 | High | Complete | ON HOLD
ART | Grasslands Tileset | Create trees | Joy | 2023-10-08 | High | Complete
ART | Grasslands Tileset | Create fences | Joy | 2023-10-08 | High | Complete
ART | Grasslands Tileset | Create lake | Joy | 2023-10-08 | Low | ON HOLD
ART | Bullet Bunny Enemy | Create idle sprite | Joy | 2023-10-18 | High | ON HOLD
ART | Bullet Bunny Enemy | Walk animation front | Joy | 2023-10-18 | High | Complete
ART | Bullet Bunny Enemy | Walk animation back | Joy | 2023-10-18 | High | Complete
ART | Bullet Bunny Enemy | Walk animation side | Joy | 2023-10-18 | High | Complete
ART | Slime? Enemy | Create idle sprite | Joy | 2023-10-25 | High | ON HOLD
ART | Slime? Enemy | Walk animation front | Joy | 2023-10-25 | High | Complete
ART | Slime? Enemy | Walk animation back | Joy | 2023-10-25 | High | Complete
ART | Slime? Enemy | Walk animation side | Joy | 2023-10-25 | High | Complete
ART | Bear Bunny Enemy | Create idle sprite | Joy | 2023-11-01 | High | ON HOLD
ART | Bear Bunny Enemy | Walk animation front | Joy | 2023-11-01 | High | ON HOLD
ART | Bear Bunny Enemy | Walk animation back | Joy | 2023-11-01 | High | ON HOLD
ART | Bear Bunny Enemy | Walk animation side | Joy | 2023-11-01 | High | ON HOLD
ART | Bear Bunny Enemy | Attack animation | Joy | 2023-11-01 | High | ON HOLD
ART | Bunnyville House | Art of a house in Bunnyville. | Joy | 2023-11-08 | Low | ON HOLD
ART | Revolver item art | Art for the revolver weapon. | Joy | 2023-11-15 | Low | ON HOLD
ART | Slingshot item art | Art for the slingshot weapon. | Joy | 2023-11-15 | Low | ON HOLD
ART | Carrot Powerup Art | Art for the carrot powerup. Grows from the ground. | Joy | 2023-11-15 | Low | OVERDUE
ART | UI Buttons | UI art for the buttons on the menus and dialogue screens. | Joy | 2023-11-15 | Low | ON HOLD
ART | UI Text Display | UI art for text boxes - instructions, dialogue, inventory, etc. | Joy | 2023-11-15 | Low | ON HOLD
ART | Title Art for Main Menu | Title art for Carrot Quest: The Root of Evil. Incorporate carrot/bunny/woodsy elements. | Joy | 2023-11-15 | Low | Complete
ART | Vagabond Bunny | Player death animation. Falls to floor. | Joy | 2023-11-22 | Low | ON HOLD
ART | Implement Art | Implement enemy animations for Bullet Bunny and Sllime. | Joy | 2023-11-22 | High | Incomplete
ART | Mountain Art | Art for mountains that will form the impassable barriers to levels. | Joy | 2023-11-22 | High | Incomplete
PROGRAMMING | Camera Scale | Fix camera to have larger graphics than pixel, adjust physics/knockback/sizes to new camera size | Brenton | 2023-09-20 | Low | Complete
PROGRAMMING | Gun Attack Fire Rate | Implement a limited gun fire rate (ideally adjustable per weapon), limited bullets, reload | Brenton | 2023-09-27 | High | Incomplete
PROGRAMMING | Reload Action | A function to press 'R' to reload the gun. Necessary after running out of bullets. | Brenton | 2023-09-27 | High | Complete
PROGRAMMING | Reload Text | A UI text element that is relatively small at top or bottom of screen. Says "Press 'R' to reload" when the player runs out of bullets. Flashes gently or draws the eye in some other way. | Brenton | 2023-10-08 | High | Complete
PROGRAMMING | Dodging Action | Press 'Space' to dodge a short distance in the movement direction. Briefly invulnerable. | Brenton | 2023-10-08 | High | Complete
PROGRAMMING | Burrowing Action | Press and hold 'Shift' to create a burrow entrance and enter the ground. On release of 'Shift', burrow exit is created and Player returns to normal state. | Brenton | 2023-10-18 | High | Complete
PROGRAMMING | Burrowing Action | While underground (holding down 'Shift'), Player is invulnerable and semi-transparent. | Brenton | 2023-10-18 | High | Complete
PROGRAMMING | Burrowing Action | When near a burrow entrance or exit, press 'E' to travel through the burrow to the other side. | Brenton | 2023-10-18 | High | Complete
PROGRAMMING | NPC Interaction | Implement the NPC Hyacinth into the game. When the Player presses 'E' next to an NPC, a dialogue box spawns. | Brenton | 2023-10-25 | High | Complete
PROGRAMMING | NPC Dialogue | Once the dialogue box spawns, text will display on it, and the Player can click or press 'E' to advance the dialogue. 'Esc' exits the dialogue.(I changed Esc to spacebar, might change it back. | Brenton | 2023-10-25 | High | Complete
PROGRAMMING | NPC Dialogue | While talking to an NPC, the Player can not fire their gun or move. They are invulnerable to attack. | Brenton | 2023-10-25 | High | Complete
PROGRAMMING | Healing Carrot Powerup | A carrot that drops from enemies and can be found in the overworld. | Brenton | 2023-11-01 | High | Complete
PROGRAMMING | Enemies Give Up | After the Player gets a certain distance from an aggroed enemy, the enemy stops pursuing them. | Brenton | 2023-11-01 | Low | Complete
PROGRAMMING | Slingshot Weapon | A new ranged weapon type added to the game. Hold to aim and release to fire, has a short range. | Brenton | 2023-11-01 | High | ON HOLD
PROGRAMMING | Slingshot Weapon | Slingshot weapon is now the starting weapon instead of the revolver. | Brenton | 2023-11-01 | High | ON HOLD
PROGRAMMING | Inventory | An inventory system where items can be picked up and then equipped. | Brenton | 2023-11-08 | High | Incomplete / 50%
PROGRAMMING | Revolver item pickup | The revolver is an item that can be found, picked up, and then equipped. | Brenton | 2023-11-08 | High | ON HOLD
PROGRAMMING | Enemy Bullets Slower | Enemy bullets slower, more distinct color. Better chance for Player to dodge. | Brenton | 2023-11-22 | Low | Complete
PROGRAMMING | NPC Dialogue | While talking to an NPC, the NPC's character art displays beside the text box. | Brenton | 2023-11-22 | High | Complete
PROGRAMMING | Sword Attack Speed | Implement a limited sword swing rate (ideally adjustable per weapon) so the sword can not be swung as fast as the player can click. | Brenton | 2023-11-22 | High | ON HOLD
SOUND | Bullet Bunny Shoot | A shooting sound for the bullet bunnies, so that the Player can tell when one is shooting at them from afar. | Brenton | 2023-10-18 | High | ON HOLD
SOUND | Bullet Bunny Aggro | A monster grunt/squeak-ish sound for when a bullet bunny becomes aggroed to the Player. | Brenton | 2023-10-18 | High | ON HOLD
SOUND | Gunfire | Shooting sounds for the player's revolver. Should not be too annoying / grating to hear. | Brenton | 2023-10-18 | High | Incomplete / 99%
SOUND | Reload Necessary | A sound like trying to fire a gun with no bullets in the chamber. A click type sound. | Brenton | 2023-10-18 | High | ON HOLD
SOUND | Reload | The sound of a gun being reloaded. | Brenton | 2023-10-25 | High | ON HOLD
SOUND | Sword slash | A 'whoosh' short of slashing sound for when a melee weapon is swung. | Brenton | 2023-10-25 | High | ON HOLD
SOUND | Bear Bunny Aggro | A monster growl sound when the bear bunny spots the Player. | Brenton | 2023-10-25 | High | ON HOLD
SOUND | Bear Bunny Attack | A monster growl/grunt when the bear bunny does its melee attack. | Brenton | 2023-10-25 | High | ON HOLD
SOUND | Slime move sounds | Slime wet sounds that play as it moves. | Brenton | 2023-10-25 | Low | ON HOLD
SOUND | Green Fields Music | A looping track for the Fields area, that relatively cheerful. | Brenton | 2023-11-01 | High | ON HOLD
SOUND | Slingshot fire sound | Twang of a slingshot shooting. | Brenton | 2023-11-01 | Low | ON HOLD
SOUND | UI interaction / Click | Click sound for interacting with UI. Not very high pitched, kind of a wood sound. | Brenton | 2023-11-01 | Low | ON HOLD
DESIGN | GDD | Fix up Game Design Document. |  | 2023-09-27 | High | Complete
DESIGN | Level 1 Layout design | Layout for obstacles and enemies in level 1. Major scene elements included in the layout as well. |  | 2023-10-18 | High | Complete
DESIGN | Level 2 Layout design | Layout for obstacles and enemies in level 2. Major scene elements included in the layout as well. |  | 2023-10-25 | High | Complete
DESIGN | Level 3 Layout design | Layout for obstacles and enemies in level 3. Major scene elements included in the layout as well. |  | 2023-11-01 | High | ON HOLD
DESIGN | Hyacinth dialogue | Write dialogue for Hyacinth to say in the turorial level. |  | 2023-11-22 | High | Incomplete