## Sheet1
Carrot Quest ASSET LIST
Department | Asset | Task | Who | Due | Priority | Status | KEY
ART | Vagabond Bunny | Walk animation front | Joy | Week 5 | High | Complete | Incomplete
ART | Vagabond Bunny | Walk animation back | Joy | Week 5 | High | Complete | Complete
ART | Vagabond Bunny | Walk animation side | Joy | Week 5 | High | Complete | OVERDUE
ART | Grasslands Tileset | Create ground tiles | Joy | Week 6 | High | Incomplete
ART | Grasslands Tileset | Create trees | Joy | Week 6 | High | Incomplete
ART | Grasslands Tileset | Create fences | Joy | Week 6 | High | Incomplete
ART | Grasslands Tileset | Create lake | Joy | Week 6 | Low | Incomplete
ART | Bullet Bunny Enemy | Create idle sprite | Joy | Week 7 | High | Incomplete
ART | Bullet Bunny Enemy | Walk animation front | Joy | Week 7 | High | Incomplete
ART | Bullet Bunny Enemy | Walk animation back | Joy | Week 7 | High | Incomplete
ART | Bullet Bunny Enemy | Walk animation side | Joy | Week 7 | High | Incomplete
ART | Slime? Enemy | Create idle sprite | Joy | Week 8 | High | Incomplete
ART | Slime? Enemy | Walk animation front | Joy | Week 8 | High | Incomplete
ART | Slime? Enemy | Walk animation back | Joy | Week 8 | High | Incomplete
ART | Slime? Enemy | Walk animation side | Joy | Week 8 | High | Incomplete
ART | Bear Bunny Enemy | Create idle sprite | Joy | Week 9 | High | Incomplete
ART | Bear Bunny Enemy | Walk animation front | Joy | Week 9 | High | Incomplete
ART | Bear Bunny Enemy | Walk animation back | Joy | Week 9 | High | Incomplete
ART | Bear Bunny Enemy | Walk animation side | Joy | Week 9 | High | Incomplete
ART | Bear Bunny Enemy | Attack animation | Joy | Week 9 | High | Incomplete
ART | Bunnyville House | Art of a house in Bunnyville. | Joy | Week 10 | Low | Incomplete
ART | Revolver item art | Art for the revolver weapon. | Joy | Week 11 | Low | Incomplete
ART | Slingshot item art | Art for the slingshot weapon. | Joy | Week 11 | Low | Incomplete
ART | Carrot Powerup Art | Art for the carrot powerup. Grows from the ground. | Joy | Week 11 | Low | Incomplete
ART | UI Buttons | UI art for the buttons on the menus and dialogue screens. | Joy | Week 12 | Low | Incomplete
ART | UI Text Display | UI art for text boxes - instructions, dialogue, inventory, etc. | Joy | Week 12 | Low | Incomplete
ART | Title Art for Main Menu | Title art for Carrot Quest: The Root of Evil. Incorporate carrot/bunny/woodsy elements. | Joy | Week 13 | Low | Complete
ART | Vagabond Bunny | Player death animation. Falls to floor. | Joy | Week 14 | Low | Incomplete
PROGRAMMING | Camera Scale | Fix camera to have larger graphics than pixel, adjust physics/knockback/sizes to new camera size | Brenton | Week 5 | Low | Incomplete
PROGRAMMING | Gun Attack Fire Rate | Implement a limited gun fire rate (ideally adjustable per weapon), limited bullets, reload | Brenton | Week 6 | High | Complete
PROGRAMMING | Reload Action | A function to press 'R' to reload the gun. Necessary after running out of bullets. | Brenton | Week 6 | High | Complete
PROGRAMMING | Reload Text | A UI text element that is relatively small at top or bottom of screen. Says "Press 'R' to reload" when the player runs out of bullets. Flashes gently or draws the eye in some other way. | Brenton | Week 7 | High | Incomplete
PROGRAMMING | Dodging Action | Press 'Space' to dodge a short distance in the movement direction. Briefly invulnerable. | Brenton | Week 7 | High | Incomplete
PROGRAMMING | Burrowing Action | Press and hold 'Shift' to create a burrow entrance and enter the ground. On release of 'Shift', burrow exit is created and Player returns to normal state. | Brenton | Week 8 | High | Incomplete
PROGRAMMING | Burrowing Action | While underground (holding down 'Shift'), Player is invulnerable and semi-transparent. | Brenton | Week 8 | High | Incomplete
PROGRAMMING | Burrowing Action | When near a burrow entrance or exit, press 'E' to travel through the burrow to the other side. | Brenton | Week 8 | High | Incomplete
PROGRAMMING | NPC Interaction | Implement the NPC Hyacinth into the game. When the Player presses 'E' next to an NPC, a dialogue box spawns. | Brenton | Week 9 | High | Incomplete
PROGRAMMING | NPC Dialogue | Once the dialogue box spawns, text will display on it, and the Player can click or press 'E' to advance the dialogue. 'Esc' exits the dialogue. | Brenton | Week 9 | High | Incomplete
PROGRAMMING | NPC Dialogue | While talking to an NPC, the Player can not fire their gun or move. They are invulnerable to attack. | Brenton | Week 9 | High | Incomplete
PROGRAMMING | Healing Carrot Powerup | A carrot growing from the ground that the Player can press 'E' on to consume, giving them 1 heart. | Brenton | Week 10 | High | Incomplete
PROGRAMMING | Enemies Give Up | After the Player gets a certain distance from an aggroed enemy, the enemy stops pursuing them. | Brenton | Week 10 | Low | Incomplete
PROGRAMMING | Slingshot Weapon | A new ranged weapon type added to the game. Hold to aim and release to fire, has a short range. | Brenton | Week 11 | High | Incomplete
PROGRAMMING | Slingshot Weapon | Slingshot weapon is now the starting weapon instead of the revolver. | Brenton | Week 11 | High | Incomplete
PROGRAMMING | Inventory | An inventory system where items can be picked up and then equipped. | Brenton | Week 12 | High | Incomplete
PROGRAMMING | Revolver item pickup | The revolver is an item that can be found, picked up, and then equipped. | Brenton | Week 12 | High | Incomplete
PROGRAMMING | Enemy Bullets Slower | Enemy bullets slower, more distinct color. Better chance for Player to dodge. | Brenton | Week 13 | Low | Incomplete
SOUND | Bullet Bunny Shoot | A shooting sound for the bullet bunnies, so that the Player can tell when one is shooting at them from afar. | Brenton | Week 7 | High | Incomplete
SOUND | Bullet Bunny Aggro | A monster grunt/squeak-ish sound for when a bullet bunny becomes aggroed to the Player. | Brenton | Week 7 | High | Incomplete
SOUND | Gunfire | Shooting sounds for the player's revolver. Should not be too annoying / grating to hear. | Brenton | Week 8 | High | Incomplete
SOUND | Reload Necessary | A sound like trying to fire a gun with no bullets in the chamber. A click type sound. | Brenton | Week 8 | High | Incomplete
SOUND | Reload | The sound of a gun being reloaded. | Brenton | Week 9 | High | Incomplete
SOUND | Sword slash | A 'whoosh' short of slashing sound for when a melee weapon is swung. | Brenton | Week 9 | High | Incomplete
SOUND | Bear Bunny Aggro | A monster growl sound when the bear bunny spots the Player. | Brenton | Week 10 | High | Incomplete
SOUND | Bear Bunny Attack | A monster growl/grunt when the bear bunny does its melee attack. | Brenton | Week 10 | High | Incomplete
SOUND | Slime move sounds | Slime wet sounds that play as it moves. | Brenton | Week 10 | Low | Incomplete
SOUND | Green Fields Music | A looping track for the Fields area, that relatively cheerful. | Brenton | Week 11 | High | Incomplete
SOUND | Slingshot fire sound | Twang of a slingshot shooting. | Brenton | Week 13 | Low | Incomplete
SOUND | UI interaction / Click | Click sound for interacting with UI. Not very high pitched, kind of a wood sound. | Brenton | Week 13 | Low | Incomplete
DESIGN | GDD | Fix up Game Design Document. | Joy | Week 6 | High | Incomplete 80%
DESIGN | Level 1 Layout design | Layout for obstacles and enemies in level 1. Major scene elements included in the layout as well. |  | Week 7 | High | Incomplete
DESIGN | Level 2 Layout design | Layout for obstacles and enemies in level 2. Major scene elements included in the layout as well. |  | Week 8 | High | Incomplete
DESIGN | Level 3 Layout design | Layout for obstacles and enemies in level 3. Major scene elements included in the layout as well. |  | Week 9 | High | Incomplete