## Sheet1
Carrot Quest ASSET LIST
Department | Asset | Task | Who | Due | Priority | Status | KEY
ART | Vagabond Bunny | Walk animation front | Joy | Week 5 | High | Incomplete | Incomplete
ART | Vagabond Bunny | Walk animation back | Joy | Week 5 | High | Incomplete | Complete
ART | Vagabond Bunny | Walk animation side | Joy | Week 5 | High | Incomplete | OVERDUE
ART | Grasslands Tileset | Create ground tiles | Joy | Week 6 | High | Incomplete
ART | Grasslands Tileset | Create trees | Joy | Week 6 | High | Incomplete
ART | Grasslands Tileset | Create fences | Joy | Week 6 | High | Incomplete
ART | Grasslands Tileset | Create lake | Joy | Week 6 | Low | Incomplete
ART | Bullet Bunny Enemy | Create idle sprite | Joy | Week 7 | High | Incomplete
ART | Bullet Bunny Enemy | Walk animation front | Joy | Week 7 | High | Incomplete
ART | Bullet Bunny Enemy | Walk animation back | Joy | Week 7 | High | Incomplete
ART | Bullet Bunny Enemy | Walk animation side | Joy | Week 7 | High | Incomplete
ART | Slime? Enemy | Create idle sprite | Joy | Week 8 | High | Incomplete
ART | Slime? Enemy | Walk animation front | Joy | Week 8 | High | Incomplete
ART | Slime? Enemy | Walk animation back | Joy | Week 8 | High | Incomplete
ART | Slime? Enemy | Walk animation side | Joy | Week 8 | High | Incomplete
ART | Bear Bunny Enemy | Create idle sprite | Joy | Week 9 | High | Incomplete
ART | Bear Bunny Enemy | Walk animation front | Joy | Week 9 | High | Incomplete
ART | Bear Bunny Enemy | Walk animation back | Joy | Week 9 | High | Incomplete
ART | Bear Bunny Enemy | Walk animation side | Joy | Week 9 | High | Incomplete
ART | Bear Bunny Enemy | Attack animation | Joy | Week 9 | High | Incomplete
PROGRAMMING | Camera Scale | Fix camera to have larger graphics than pixel, adjust physics/knockback/sizes to new camera size | Brenton | Week 5 | High | Incomplete
PROGRAMMING | Gun Attack | Implement a limited gun fire rate (ideally adjustable per weapon), limited bullets, reload | Brenton | Week 6 | High | Incomplete
PROGRAMMING | Reload Action | A function to press 'R' to reload the gun. Necessary after running out of bullets. | Brenton | Week 6 | High | Incomplete
PROGRAMMING | Dodging Action | Press 'Space' to dodge a short distance in the movement direction. Briefly invulnerable. | Brenton | Week 7 | High | Incomplete
PROGRAMMING | Burrowing Action | Press and hold 'Shift' to create a burrow entrance and enter the ground. On release of 'Shift', burrow exit is created and Player returns to normal state. | Brenton | Week 8 | High | Incomplete
PROGRAMMING | Burrowing Action | While underground (holding down 'Shift'), Player is invulnerable and semi-transparent. | Brenton | Week 8 | High | Incomplete
PROGRAMMING | NPC Interaction | Implement the NPC Hyacinth into the game. When the Player presses 'E' next to an NPC, a dialogue box spawns. | Brenton | Week 9 | High | Incomplete
PROGRAMMING | NPC Dialogue | Once the dialogue box spawns, text will display on it, and the Player can click or press 'E' to advance the dialogue. 'Esc' exits the dialogue. | Brenton | Week 9 | High | Incomplete
PROGRAMMING | NPC Dialogue | While talking to an NPC, the Player can not fire their gun or move. They are invulnerable to attack. | Brenton | Week 9 | High | Incomplete
PROGRAMMING |  |  | Brenton | Week 10 | High | Incomplete
PROGRAMMING |  |  | Brenton | Week 11 | High | Incomplete
PROGRAMMING |  |  | Brenton | Week 12 | High | Incomplete
PROGRAMMING |  |  | Brenton | Week 13 | High | Incomplete
PROGRAMMING |  |  | Brenton | Week 14 | High | Incomplete